## Timeline for New School Prep
AF School Startup Checklist
|  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
| STATUS | [12 empty] | start date | due date | task owner
TEAM X
Incorporation
Recruit and assemble Board of Trustees | Incomplete | [12 empty] | 2007-01-01 | 2007-04-30 | AF Director of External Relations, NY
Apply for Federal Employer Identification Number (FEIN) | Incomplete | [12 empty] | 2007-04-01 | 2007-04-30 | AF Director of External Relations, NY
Incorporate school (working with corporate counsel) | Incomplete | [12 empty] | 2007-03-01 | 2007-05-15 | AF Director of External Relations, NY
File application for 501(c)(3) status (working with corporate counsel) | Incomplete | [12 empty] | 2007-03-01 | 2007-05-15 | AF Director of External Relations, NY
Register school with State Attorney General's Office | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of External Relations, NY
Tax-exemption
File application for state tax exemption | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of NY Operations
Trademarks & Copyrights
File trademark and copyright applications (working with corporate counsel) | Incomplete | [12 empty] | 2007-06-01 | 2007-07-15 | AF Director of External Relations, NY
Supplement initial filing with new school logos, etc. (working with corporate counsel) | Incomplete | [12 empty] | 2007-09-01 | 2007-09-30 | NY Director of External Relations
Employee Policies
Draft employee policies for review/adoption by Board of Trustees | Incomplete | [12 empty] | 2007-03-01 | 2007-05-15 | AF Chief Operating Officer
Student Recruitment
Outreach to local community-based organizations for help with recruitment | Incomplete | [12 empty] | 2007-01-01 | 2007-03-01 | AF Director of External Relations, NY
Meet with local Superintendentand and area school leaders | Incomplete | [12 empty] | 2007-01-01 | 2007-03-01 | AF Director of External Relations, NY
Request mailing labels from district for recruitment mailing | Incomplete | [12 empty] | 2007-01-01 | 2007-03-15 | AF Director of External Relations, NY
Deploy recruitment mailing & conduct follow-up | Incomplete | [12 empty] | 2007-03-01 | 2007-03-01 | AF Director of External Relations, NY
Develop plan/format/presentation for AF Open Houses | Incomplete | [12 empty] | 2007-03-01 | 2007-03-15 | AF Director of External Relations, NY
Circulate/Post recruitment posters | Incomplete | [12 empty] | 2007-03-01 | 2007-03-15 | AF Director of External Relations, NY
Research and present at/attend key community functions | Incomplete | [12 empty] | 2007-01-01 | 2007-04-15 | AF Director of External Relations, NY
Open House 1 | Incomplete | [12 empty] | 2007-03-10 | 2007-03-10 | AF Director of External Relations, NY/School Leader
Open House 2 & 3 | Incomplete | [12 empty] | 2007-03-17 | 2007-03-28 | AF Director of External Relations, NY/School Leader
Student Lottery & Enrollment
Plan Lottery (location, equipment/supplies, refreshments, third-party monitor) | Incomplete | [12 empty] | 2007-03-01 | 2007-03-31 | AF Director of External Relations
Conduct Lottery | Incomplete | [12 empty] | 2007-04-16 | 2007-04-16 | AF Director of External Relations
Contact parents and schedule students for placement testing | Incomplete | [12 empty] | 2007-04-16 | 2007-05-31 | Director of School Operations/School Registrar
Parent Meetings & Placement Testing | Incomplete | [12 empty] | 2007-06-01 | 2007-07-31 | Director of School Operations/School Registrar
Secure standardized test scores and other student data from the district | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | Director of School Operations/School Registrar
Student Enrollment (collect required documentation, log into SIS) | Incomplete | [12 empty] | 2007-04-16 | 2007-08-31 | School Registrar
Students evaluated for Special Education Services needs in coordination with local CSE | Incomplete | [12 empty] | 2007-04-16 | 2007-07-30 | AF Director of Special Education
Develop Family Handbook (incl FERPA, FOIL, Open Mtgs) and distribute to new families | Incomplete | [12 empty] | 2007-04-01 | 2007-08-15 | AF Director of NY Operations/School Leader
Students assigned to classes (teachers provided with class rosters) | Incomplete | [12 empty] | 2007-07-01 | 2007-08-04 | School Leader/Deans
TEAM FACILITIES
Facility Planning
Establish Site Criteria (short-term and long-term) | Incomplete | [12 empty] | 2007-03-01 | 2007-03-15 | AF Chief Operating Officer
Identify site / acquire site | Incomplete
Conduct Site Visits (short-term facility) | Incomplete | [12 empty] | 2007-03-15 | 2007-04-30 | AF Director of NY Operations
Finalize Site & Occupation Schedule, sign leases (short-term & long-term facility) | Incomplete | [12 empty] | 2007-05-01 | 2007-05-31 | AF Director of NY Operations
Develop construction schedule and budget | Incomplete
Secure Certificate of Occupancy (if applicable) | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of NY Operations
Seek reulatory approvals (zoning, site plan) | Incomplete
Hire architect and develop design | Incomplete
Bid construction contract, select, and oversee contractors | Incomplete
School input on major design decisions (building layout and intended usage, location of plumbing, location of outlets, look and feel) | Incomplete
Site Prep (arrange for/manage reno, upgrades, ongoing maintenance services) | Incomplete | [12 empty] | 2007-06-01 | 2007-08-15 | AF Director of NY Operations
Develop and place furniture order (with school input) | Incomplete | [12 empty] | Jan | Feb
Develop and start plan for facility management | Incomplete | [12 empty] | Jan | Feb
Oversee construction and budget | Incomplete | [12 empty] | March | May
Interview, select and onboard facility manager | Incomplete | [12 empty] | March | May
Health Inspection (if non-DOE site) | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of NY Operations
Fire Inspection (if non-DOE site) | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of NY Operations
Oversee construction closeout and punchlist | Incomplete | [12 empty] | June | July
Oversee furniture delivery and installation | Incomplete | [12 empty] | June | July
Establish building utility accounts | Incomplete | [12 empty] | June | July
Establish building service accounts | Incomplete | [12 empty] | June | July
Bind property insurance coverage | Incomplete | [12 empty] | June | July
Oversee start of facility manager | Incomplete | [12 empty] | June | July
Coordinate turnover from Facilities Team to Ops Team | Incomplete | [12 empty] | June | July
Coordinate construction punchlist and warranty work | Incomplete | [12 empty] | August | December
TEAM OPS
General
Establish School Calendar (2007-2008 School Year) | Incomplete | [12 empty] | 2007-03-01 | 2007-03-30 | AF Superintendent/School Leader
Establish School Schedule (start-time, end-time, after school, etc.) | Incomplete | [12 empty] | 2007-03-01 | 2007-03-30 | AF Superintendent/School Leader
Insurance
Procure and activate commercial insurance (liability/property/directors' coverage) for school | Incomplete | [12 empty] | 2007-04-15 | 2007-07-01 | AF Chief Operating Officer
Activate student accident & medical policy & non-owned auto coverage | Incomplete | [12 empty] | 2007-08-01 | 2007-08-25 | AF Chief Operating Officer
Transportation
Contact the Office of Pupil Transportation to request student transportation services | Incomplete | [12 empty] | 2007-04-15 | 2007-04-30 | AF Director of NY Operations
Research and procure special event/after school transportation services | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of NY Operations
Enter student roster into ATS to determine eligibility for transportation services (OPT) | Incomplete | [12 empty] | 2007-07-01 | 2007-07-15 | Director of School Operations
Food
Contact Office of School Food and Nutrition Services to request food services for site | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Ops
Ensure families properly complete Free/Reduced Lunch Application and determine eligibility | Incomplete | [12 empty] | 2007-08-01 | 2007-08-30 | Director of School Operations/School Registrar
Research and procure auxillary food services (snacks) in the area | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of NY Operations/Director of School Operations
Health
Contact Dept of Health and Mental Hygiene Regional Office to request/procure Nursing Services | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of NY Operations
Document immunization requirements and train Director of School Operations in requirements | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of NY Operations/Director of School Operations
Research free medical clinics in school community | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of NY Operations
Notify parents of immunization requirements and options for compliance | Incomplete | [12 empty] | 2007-06-15 | 2007-06-30 | AF Ops
Payroll
Establish payroll account for school and ensure that Director of School Operations is trained | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of Finance
School Safety
Research and draft school safety plan (include schedule of required drills, etc.) | Incomplete | [12 empty] | 2007-06-01 | 2007-07-01 | AF Director of NY Operations/Director of School Operations
Develop concise disaster/emergency plan for use by school leadership in the event of catastrophe | Incomplete | [12 empty] | 2007-04-01 | 2007-05-30 | AF Chief Operating Officer
Train school leaders in safety/emergency plans | Incomplete | [12 empty] | 2007-08-01 | 2007-08-15 | AF Chief Operating Officer
School Reporting Requirements
Document school reporting requirements and train Director of School Operations (as point person) | Incomplete | [12 empty] | 2007-04-01 | 2007-07-31 | AF Chief Operating Officer/Director of School Operations
Vendors & Accounts
Submit credit applications with key vendors upon chartering (based on Master Order List (MOL)) | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of NY Operations/Director of School Operations
Establish service and vendor accounts for school | Incomplete | [12 empty] | 2007-05-15 | 2007-06-01 | AF Director of NY Operations/Director of School Operations
Purchase Orders
Generate comprehensive list(s) of school start-up supply needs (using MOL database) | Incomplete | [12 empty] | 2007-05-01 | 2007-05-01 | Director of School Operations
Create all purchase orders for school (textbooks, software, supplies) | Incomplete | [12 empty] | 2007-06-01 | 2007-06-15 | Director of School Operations
Place orders | Incomplete | [12 empty] | 2007-06-01 | 2007-07-15 | Director of School Operations
TEAM IT
IT
Fill out Tech Needs template (school readiness questions and hardware needs) | Incomplete
Draft IT/Telcom plan for school | Incomplete | [12 empty] | 2007-03-15 | 2007-05-15 | AF Director of IT
Draft Purchase Orders for systems hardware | Incomplete | [12 empty] | 2007-06-01 | 2007-06-15 | NY IT Team Lead
Implement IT plan at school facility | Incomplete | [12 empty] | 2007-07-01 | 2007-08-15 | NY IT Team Lead
TEAM HUMAN CAPITAL
Staff Recruitment/Onboarding
Recruit and Train School Leaders (Principal and Deans) | Incomplete | [12 empty] | 2007-09-01 | 2007-08-15 | AF Superintendent/AF President
Define and implement school-specific Teacher Recruitment Plan (incl. teacher certification reqs) | Incomplete | [12 empty] | 2007-11-15 | 2007-07-30 | AF Superintendent/NY Recruitment Team Lead
Develop compensation scales for teachers/administrators | Incomplete | [12 empty] | 2007-01-01 | 2007-03-15 | AF Superintendent/CFO
New Staff Training | Incomplete | [12 empty] | 2007-08-04 | 2007-08-15 | AF Superintendent/School Leader
Ensure compliance with finger printing and background check procedures/protocols | Incomplete | [12 empty] | 2007-06-01 | 2007-07-30 | AF Director of NY Operations
Compile Staff Registration Packet (all non-instructional requirements, forms, policies/handbooks)) | Incomplete | [12 empty] | 2007-04-01 | 2007-04-15 | AF Director of NY Operations
Recruit and hire Director of Operations | Incomplete | [12 empty] | 2007-03-01 | 2007-04-15 | AF Director of NY Operations
Recruit and hire Registrar | Incomplete | [12 empty] | 2007-03-01 | 2007-04-15 | AF Director of NY Operations
School Operations Team Training | Incomplete | [12 empty] | 2007-05-01 | 2007-08-01 | AF Chief Operating Officer/Director of NY Operations
Recruit & hire school-based IT Associate | Incomplete | [12 empty] | 2007-05-01 | 2007-06-15 | AF Director of IT/NY IT Team Lead
Process/register all new school employees | Incomplete | [12 empty] | 2007-07-01 | 2007-08-15 | Director of School Operations
Secure cell phone plans for principals, deans, and operations team | Incomplete | [12 empty] | 2007-06-15 | 2007-06-30 | Director of School Operations
Employee Benefits
Finalize benefits providers | Incomplete | [12 empty] | 2007-03-01 | 2007-05-15 | AF Chief Operating Officer/CFO
Enroll all school staff in insurance and benefits | Incomplete | [12 empty] | 2007-07-01 | 2007-08-15 | School Director of Operations
Teacher Certification
Conduct teacher certification audit - define certification plan for all uncertified instructional staff | Incomplete | [12 empty] | 2007-08-01 | 2007-08-30 | Director of School Operations/School Leader
School Specific Staff Policies
Think through atypical hires (hybrid roles, reduced schedules) | Incomplete | [12 empty] | 2011-05-01 | 2011-07-30 | Principal
New staff paper work | Incomplete | [12 empty] | through May | July | Director of School Operations
HRIS set-up | Incomplete | [12 empty] | through May |  | Director of School Operations
Set-up personnel files, orer labor laws posters | Incomplete | [12 empty] | through May |  | Director of School Operations
Benefits set-up (health, vision, retirement) | Incomplete | [14 empty] | Director of School Operations
Onboarding (e.g. benefits, payroll, laptop) | Incomplete | [12 empty] | June | July | Director of School Operations
TEAM FINANCE
Accounting
Research and identify area accounting firm and auditor for approval/adoption by Board of Trustees | Incomplete | [12 empty] | 2007-03-01 | 2007-04-30 | AF Director of Finance/CFO
Present proposed fiscal policies and procedures for adoption by Trustees | Incomplete | [12 empty] | 2007-05-15 | 2007-07-15 | CFO
Financial Software | Incomplete
Implement AF Financial Management System | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of Finance
Implement AF chart of accounts | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of Finance
Implement AF Bookkeeping procedures | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of Finance
Banking
Establish checking and business investment accounts | Incomplete | [12 empty] | 2007-05-01 | 2007-06-30 | CFO
Apply for line of credit | Incomplete | [12 empty] | 2007-05-01 | 2007-06-30 | CFO
Secure corporate credit cards for school leadership | Incomplete | [12 empty] | 2007-06-01 | 2007-06-30 | AF Director of Finance
Budget
Research and confirm revenue projections (public funding) | Incomplete | [12 empty] | 2007-03-01 | 2007-04-30 | AF Director of Finance
Document billing/invoicing/reporting schedule for per pupil and other public revenues | Incomplete | [12 empty] | 2007-05-01 | 2007-05-15 | AF Director of Finance
Draft and finalize school budget (derived from AF budget model) for approval by Board of Trustees | Incomplete | [12 empty] | 2007-04-15 | 2007-07-15 | CFO/School Leader
TEAM TEACHING & LEARNING
Teaching & Learning
Kick-off meeting with Nancy Livingston | Incomplete | [12 empty] | Jan
Math curriculum selection, review of scope and sequences, review of resources of Better Lesson | Incomplete | [12 empty] | March
ELA Program Design | Incomplete | [12 empty] | March
Curriculum ordering using the MOL | Incomplete | [12 empty] | April
Curriculum based PD planning | Incomplete | [12 empty] | May
New Staff Training | Incomplete | [12 empty] | July
Special Education
Research Special Ed & Related Services Providers/recruitment channels for Special Ed Certified educators | Incomplete | [12 empty] | 2007-04-01 | 2007-05-30 | AF Director of Special Education
Verify and document Special Ed revenue formula | Incomplete | [12 empty] | 2007-04-01 | 2007-04-15 | AF Director of Special Education/AF Director of Finance
Develop Special Ed Services plan for school | Incomplete | [12 empty] | 2007-05-01 | 2007-05-30 | AF Director of Special Education
Contract with providers/secure appropriate staff for provision of services to students in need | Incomplete | [12 empty] | 2007-06-01 | 2007-07-30 | AF Director of Special Education
Student Software orders (Digital Learning) | Incomplete
TEAM MARKETING
PR/Communications
Public Announcement about School | Incomplete | [12 empty] | 2007-04-17 | 2007-04-17 | Director of External Relations, NY
School Opening Ceremony | Incomplete | [12 empty] | 2007-09-15 | 2007-09-15 | Director of External Relations, NY
Finalize designs for student recruitment materials | Incomplete | [13 empty] | 2007-03-01 | AF Communications Officer
Finalize logo designs for school apparell and uniforms | Incomplete | [12 empty] | 2007-03-01 | 2007-04-30 | AF Communications Officer
Develop and produce school letterhead, etc. | Incomplete | [12 empty] | 2007-03-01 | 2007-04-30 | AF Communications Officer
Design and produce business cards for school staff | Incomplete | [12 empty] | 2007-06-01 | 2007-07-30 | AF Communications Officer